## Projects
Project ID | Project Name | DoD Division | Requestor / POC | Designer Assigned | Status | Revision Round | Approval Status | Date Requested | Due Date | Date Delivered | Notes
GP-001 | Recruitment Poster Series | Army | SFC J. Smith |  | Intake | 0 | Pending | 2026-05-01 | 2026-05-20 |  | Awaiting brand assets from requestor
GP-002 | Annual Report Infographics | Navy | LT M. Johnson | A. Designer | Design | 0 | Pending | 2026-04-22 | 2026-05-15 |  | Five infographics; data due 05-08
GP-003 | Squadron Patch Update | Air Force | Capt R. Davis | B. Designer | Review | 1 | In Review | 2026-04-10 | 2026-05-10 |  | Embroidery vendor specs attached
GP-004 | Recruiting Booth Banners | Marines | GySgt T. Martinez | A. Designer | Revision | 2 | Changes Requested | 2026-03-28 | 2026-05-12 |  | Color match issue on red — proof reprint
GP-005 | Mission Patch Concept | Space Force | Maj L. Chen | C. Designer | Approved | 1 | Approved | 2026-03-15 | 2026-05-01 |  | Awaiting print vendor PO
GP-006 | Safety Campaign Posters | Coast Guard | LCDR P. Nguyen | B. Designer | Delivered | 2 | Approved | 2026-02-20 | 2026-04-25 | 2026-04-24 | Final files archived in /deliverables

## Reference
Field | Allowed values
DoD Division | Army ¦ Navy ¦ Air Force ¦ Marines ¦ Space Force ¦ Coast Guard
Status | Intake ¦ Design ¦ Review ¦ Revision ¦ Approved ¦ Delivered
Approval Status | Pending ¦ In Review ¦ Changes Requested ¦ Approved ¦ Rejected
Revision Round | Whole number, 0 or greater